## 1. Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US_01 | As a developer, I want to collect and preprocess KYC data (Aadhaar, bills) so that AI models can use clean input | Must Have | Data availability | Deeksha H.S | Completed
Sprint 2 | Sprint 2 | US_02 | As a data scientist, I want to build AI models (NLP, CNN, GNN) for identity and address verification | Must Have | Cleaned data from Sprint 1 | Deeksha H.S | Completed
Sprint 3 | Sprint 3 | US_03 | As a compliance analyst, I want to integrate fraud detection pipeline with AML/KYC systems for real-time validation | Should Have | Model outputs | Deeksha H.S | Completed
Sprint 4 | Sprint 4 | US_04 | As a user, I want a web dashboard to upload documents and visualize fraud results | Must Have | Backend APIs | Deeksha H.S | Completed
Sprint 4 | Sprint 4 | US_05 | As a developer, I want to deploy the full pipeline and validate results with synthetic Aadhaar data | Must Have | All previous sprints | Deeksha H.S | Completed

## 2. Sprint Backlog
US_ID | Task ID | Task Description | Task Start Date | Task Completion Date | Developer Name | Activity | Status | Original Estimate Effort (Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US_02 | T_01 | Build OCR extraction module | 15/10/2025 | 17/10/2025 | Deeksha H.S | Development | Completed | 8 | Day 1: Done; Day 2: Done
US_02 | T_02 | Fine-tune NLP model for address verification | 18/10/2025 | 22/10/2025 | Deeksha H.S | Model Training | Completed | 12 | Day 2: Done; Day 3: Done; Day 4: Done
US_02 | T_03 | Train CNN model to detect document tampering | 23/10/2025 | 26/10/2025 | Deeksha H.S | Model Training | Completed | 10 | Day 3: Done; Day 4: Done; Day 5: Done
US_02 | T_04 | Train GNN model to detect duplicate Aadhaar identities | 27/10/2025 | 31/10/2025 | Deeksha H.S | Research/Implementation | Completed | 14 | Day 4: Done; Day 5: Done; Day 6: Done; Day 7: Done
US_02 | T_05 | Validate models and compare accuracy | 2025-01-11 | 2025-03-11 | Deeksha H.S | Testing | Completed | 6 | Day 7: Done; Day 8: Done; Day 9: Done; Day 10: Done

## 3. Daily StandUp Report
Sprint | Day | Impediments | Action Taken
Sprint 3 | Day 1 | Streamlit modules not integrating properly with AI pipeline | Refactored code, modularized OCR/NLP/CNN functions, ensured correct imports
Sprint 3 | Day 2 | Fraud detection (CNN/GNN) inference very slow in Colab | Optimized preprocessing, reduced model size, enabled batch inference
Sprint 3 | Day 3 | Missing AML rule dataset for fraud detection testing | Created synthetic AML rules (duplicate Aadhaar, age mismatch, multi-account rules)
Sprint 3 | Day 4 | Ngrok + Streamlit deployment failing due to timeout / port issues | Reconfigured port settings, restarted ngrok, ensured correct Streamlit server address
Sprint 3 | Day 5 | Everything functional | Proceeded with testing pipeline

## 4. Sprint Retrospective
SL. | Sprint | Sprint start date | Sprint end date | Developer Name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 4 | 20/10/2025 | 2025-04-11 | Deeksha H.S | Start refining Streamlit UI with better layouts and validations | Stop relying on repeated manual testing for each change | Continue enhancing user-friendly dashboard components | Added improved UI layout, error messages, validation screens
2 | Sprint 4 | 20/10/2025 | 2025-04-11 | Deeksha H.S | Start optimizing AI model inference (CNN/GNN) for faster fraud detection | Stop using temporary print statements for debugging | Continue optimizing code modularity | Implemented caching, reduced latency, cleaned all debug logs
3 | Sprint 4 | 20/10/2025 | 2025-04-11 | Deeksha H.S | Start stabilizing Ngrok/Cloudflare deployment in Google Colab | Stop restarting Streamlit server manually after changes | Continue improving deployment reliability | Fixed port issues, stabilized tunneling, ensured consistent public access
4 | Sprint 4 | 20/10/2025 | 2025-04-11 | Deeksha H.S | Start improving fraud detection logic (AML rules, duplicate detection, scoring) | Stop using local/sample datasets without preprocessing | Continue refining fraud scoring pipeline | Added AML dataset, implemented duplicate identity logic, improved final fraud score computation

## 5. Defect Tracker
SI No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | Deeksha H.S | 18/10/2025 | OCR module not extracting complete Aadhaar address | Sprint 1 | Deeksha H.S | Functional | Improved preprocessing, added custom Tesseract config for multi-line + increased DP | 19/10/2025 | Closed | Verified successfully
2 | Deeksha H.S | 22/10/2025 | NLP similarity scores inconsistent for address verification | Sprint 2 | Deeksha H.S | Algorithmic | Tuned Sentence-BERT thresholds, normalized embeddings, re-evaluated text cleaning | 23/10/2025 | Closed | Accuracy improved
3 | Deeksha H.S | 26/10/2025 | Streamlit UI not showing fraud prediction outputs (JSON mismatch) | Sprint 2 | Deeksha H.S | UI/Integration | Fixed JSON parsing, corrected variable names, updated Streamlit state update logic | 27/10/2025 | Closed | UI functioning correctly
4 | Deeksha H.S | 30/10/2025 | GNN model showing NaN values during training | Sprint 2 | Deeksha H.S | Model Training | Removed null graph edges, applied normalization, stabilized training loop | 31/10/2025 | Closed | Stable model output
5 | Deeksha H.S | 2025-03-11 | AML check module failing on duplicate address input | Sprint 3 | Deeksha H.S | Logic | Added address hashing + similarity matching to detect duplicates | 2025-04-11 | Closed | Verified via testing
6 | Deeksha H.S | 2025-06-11 | Streamlit upload form accepting unsupported formats (PDF, DOC) | Sprint 3 | Deeksha H.S | UI/Validation | Added MIME type restrictions, implemented error popup for invalid uploads | 2025-07-11 | Closed | User-friendly validation added
7 | Deeksha H.S | 2025-10-11 | Streamlit app slow due to heavy CNN/GNN processing | Sprint 3 | Deeksha H.S | Performance | Added caching, reduced preprocessing overhead, optimized inference | 2025-11-11 | Closed | App is 30–40% faster
8 | Deeksha H.S | 14/11/2025 | Dashboard graphs not updating after model output changes | Sprint 4 | Deeksha H.S | Integration | Refreshed Streamlit session state logic, ensured live updates | 15/11/2025 | Closed | Dashboard sync fixed
9 | Deeksha H.S | 18/11/2025 | Fraud alerts panel not showing latest alerts | Sprint 4 | Deeksha H.S | Functional | Fixed audit log retrieval, ensured auto-refresh every 5 seconds | 19/11/2025 | Closed | Alerts visible
10 | Deeksha H.S | 21/11/2025 | Minor alignment & UI layout issues in Streamlit | Sprint 4 | Deeksha H.S | UI | Adjusted CSS, added spacing, refined element alignment | 22/11/2025 | Closed | Presentation-ready